## Lists
Not Started | Critical | Phase 1 - Foundation | All
In Progress | High | Phase 2 - Core Operations | All (varies by source type)
Blocked | Medium | Phase 3 - Finance & Control | Owned Only
Done | Low | Phase 4 - Integrations & BI | Rented Only
Deferred |  |  | Rider-Owned Only
Owned + Rented

## Overview
3PL Mixed-Fleet System Build Checklist
[5 empty] | Total Tasks | In Progress
Purpose | This workbook converts the mixed-fleet system design into a practical task tracker and logic checklist for HR, Operations, Fleet, Finance, Compliance, Integrations, and BI. |  |  |  | 109 | 0
[5 empty] | Completed | Blocked
How to use |  |  |  |  | 0 | 0
1) Update Owner, Target Date, Status and Notes in the Master Tracker.
| 2) Use the module tabs as linked reference views by department. |  |  |  | Completion %
| 3) Review the Logic Register before development to lock core rules. |  |  |  | 0%
4) Vehicle source types assumed: RENTED_BY_COMPANY, OWNED_BY_COMPANY, RIDER_OWNED.
Module Progress Summary |  |  |  | Status Legend
Module | Total Tasks | Done | % Complete | Not Started
Data Model | 18 | 0 | 0% | In Progress
HR | 14 | 0 | 0% | Blocked
Operations | 14 | 0 | 0% | Done
Fleet | 15 | 0 | 0% | Deferred
Finance | 15 | 0 | 0%
Compliance | 12 | 0 | 0%
Integrations | 10 | 0 | 0%
BI & Reports | 11 | 0 | 0%
Last updated | 2026-04-18 13:14

## Master Tracker
Master Tracker
Source-of-truth execution tracker. Update Status, Owner, Target Date and Notes here; department tabs reference this sheet.
Checklist | Task ID | Module | Workstream | Task | Deliverable / Logic | Source Type Impact | Priority | Phase | Dependency | Status | Owner | Target Date | Notes
☐ | T-001 | Data Model | Core Entities | Define master ID strategy and audit fields across all tables | Common primary keys, created/updated timestamps, soft delete and source tracking | All | Critical | Phase 1 - Foundation |  | Not Started
☐ | T-002 | Data Model | Core Entities | Create Riders entity and base profile fields | Personal details, license, visa, bank, status and rider category | All | Critical | Phase 1 - Foundation |  | Not Started
☐ | T-003 | Data Model | Core Entities | Create Vehicles entity with mixed-fleet attributes | Plate, make/model, status, compliance dates and current assignment | All | Critical | Phase 1 - Foundation |  | Not Started
☐ | T-004 | Data Model | Mixed Fleet Logic | Add vehicle_source_type enumeration | RENTED_BY_COMPANY, OWNED_BY_COMPANY, RIDER_OWNED | All | Critical | Phase 1 - Foundation |  | Not Started
☐ | T-005 | Data Model | Mixed Fleet Logic | Create Vehicle_Source_Details entity | Ownership, supplier, purchase/rent cost, responsibilities and contract dates | All (varies by source type) | Critical | Phase 1 - Foundation |  | Not Started
☐ | T-006 | Data Model | Assignments | Create Rider_Vehicle_Assignments history table | Track assignment start/end, aggregator, client and reason for reassignment | All | Critical | Phase 1 - Foundation |  | Not Started
☐ | T-007 | Data Model | Commercial Data | Create Clients entity | 3PL customer / legal entity records for multi-client support | All | High | Phase 1 - Foundation |  | Not Started
☐ | T-008 | Data Model | Commercial Data | Create Aggregators entity | Talabat, Jahez, Keeta and any future partner configuration | All | Critical | Phase 1 - Foundation |  | Not Started
☐ | T-009 | Data Model | Commercial Data | Create Contracts entity | Rates, validity dates, billing terms and service rules by client / aggregator | All | Critical | Phase 2 - Core Operations |  | Not Started
☐ | T-010 | Data Model | Operations Data | Create Shifts entity | Shift types, scheduled hours, attendance linkage and allocation rules | All | High | Phase 2 - Core Operations |  | Not Started
☐ | T-011 | Data Model | Operations Data | Create Attendance entity | GPS check-in/out, worked hours, exceptions and approval status | All | Critical | Phase 2 - Core Operations |  | Not Started
☐ | T-012 | Data Model | Operations Data | Create Orders entity | External order ID, rider, vehicle, distance, revenue, payout and source import batch | All | Critical | Phase 2 - Core Operations |  | Not Started
☐ | T-013 | Data Model | Fleet Data | Create Maintenance_Events entity | Service/repair/accident records with paid_by and recovered_from fields | All (varies by source type) | Critical | Phase 3 - Finance & Control |  | Not Started
☐ | T-014 | Data Model | Finance Data | Create Payroll entity | Fixed pay, per-order pay, allowances, deductions, advances and net pay | All (varies by source type) | Critical | Phase 3 - Finance & Control |  | Not Started
☐ | T-015 | Data Model | Finance Data | Create Finance_Ledger / cost allocation structure | Map vehicle, rider, supplier and aggregator transactions for reporting | All | High | Phase 3 - Finance & Control |  | Not Started
☐ | T-016 | Data Model | Risk & Controls | Create Incidents / accidents entity | Capture incident type, responsibility, cost recovery and downtime impact | All | High | Phase 2 - Core Operations |  | Not Started
☐ | T-017 | Data Model | Risk & Controls | Define master status enums for riders, vehicles, orders and compliance | Ensure controlled values and reusable logic across modules | All | High | Phase 1 - Foundation |  | Not Started
☐ | T-018 | Data Model | Security | Design user roles and permission matrix | HR, Ops, Fleet, Finance, Compliance, Admin and Executive access rights | All | High | Phase 1 - Foundation |  | Not Started
☐ | T-019 | HR | Onboarding | Define rider onboarding workflow | Steps from application to activation including document approval | All | Critical | Phase 1 - Foundation |  | Not Started
☐ | T-020 | HR | Onboarding | Create rider category rules based on transport model | Different handling for company-bike riders vs rider-owned riders | All (varies by source type) | Critical | Phase 1 - Foundation |  | Not Started
☐ | T-021 | HR | Onboarding | Build document collection checklist | CPR/ID, visa, license, contract, bank, emergency contact | All | High | Phase 1 - Foundation |  | Not Started
☐ | T-022 | HR | Contracts | Prepare employment / service contract templates | Separate clauses for company vehicle, rented vehicle and rider-owned vehicle cases | All (varies by source type) | High | Phase 1 - Foundation |  | Not Started
☐ | T-023 | HR | Contracts | Capture deposit / deduction agreements where applicable | Vehicle damage, uniform, equipment or advance recovery logic | Owned + Rented | High | Phase 2 - Core Operations |  | Not Started
☐ | T-024 | HR | Compliance | Track visa and license expiry alerts | Prevent activation of riders with invalid legal documents | All | Critical | Phase 1 - Foundation |  | Not Started
☐ | T-025 | HR | Payroll Inputs | Define pay components and earning rules | Fixed salary, per-order, extra km, allowance, deductions and incentives | All (varies by source type) | Critical | Phase 2 - Core Operations |  | Not Started
☐ | T-026 | HR | Payroll Inputs | Define own-bike allowance policy | When and how rider-owned vehicle riders receive transport allowance | Rider-Owned Only | High | Phase 3 - Finance & Control |  | Not Started
☐ | T-027 | HR | Payroll Inputs | Define company-bike deduction policy | Monthly/daily deduction or damage recovery for company vehicles | Owned + Rented | High | Phase 3 - Finance & Control |  | Not Started
☐ | T-028 | HR | Attendance | Design attendance approval flow | Missed check-in, manual override, lateness and supervisor approval | All | High | Phase 2 - Core Operations |  | Not Started
☐ | T-029 | HR | People Ops | Create disciplinary process linked to vehicle misuse | Late return, reckless use, damage and repeated non-compliance | Owned + Rented | Medium | Phase 3 - Finance & Control |  | Not Started
☐ | T-030 | HR | People Ops | Create offboarding checklist | Final payroll, asset return, account disablement and document archive | All | High | Phase 3 - Finance & Control |  | Not Started
☐ | T-031 | HR | People Ops | Design leave / absence handling | Link leave status to roster and payroll | All | Medium | Phase 2 - Core Operations |  | Not Started
☐ | T-032 | HR | Dashboard | Define HR dashboard metrics | Headcount, active riders, expired docs, churn and payroll exceptions | All | Medium | Phase 4 - Integrations & BI |  | Not Started
☐ | T-033 | Operations | Shift Planning | Build shift planning and roster structure | Daily/weekly rider scheduling by client and aggregator | All | Critical | Phase 2 - Core Operations |  | Not Started
☐ | T-034 | Operations | Shift Planning | Create rider eligibility check before shift activation | Only activate riders with valid docs and approved vehicle | All | Critical | Phase 2 - Core Operations |  | Not Started
☐ | T-035 | Operations | Allocation | Design rider allocation rules by aggregator | Talabat / Jahez / Keeta assignment logic and eligibility mapping | All | Critical | Phase 2 - Core Operations |  | Not Started
☐ | T-036 | Operations | Allocation | Build rider + vehicle pairing workflow | Assign compliant available vehicle to rider for active shift | Owned + Rented | High | Phase 2 - Core Operations |  | Not Started
☐ | T-037 | Operations | Live Control | Design live operations control tower view | Online riders, active orders, issues, idle riders and replacement needs | All | High | Phase 4 - Integrations & BI |  | Not Started
☐ | T-038 | Operations | Live Control | Create breakdown escalation workflow | Different path for owned, rented and rider-owned vehicle incidents | All (varies by source type) | Critical | Phase 2 - Core Operations |  | Not Started
☐ | T-039 | Operations | Attendance | Connect attendance to operations roster | Show no-shows, late arrivals and active shift status in ops view | All | High | Phase 2 - Core Operations |  | Not Started
☐ | T-040 | Operations | Orders | Create manual order import fallback process | CSV/manual upload when API is unavailable | All | Medium | Phase 2 - Core Operations |  | Not Started
☐ | T-041 | Operations | Orders | Define order reconciliation process | Validate order count, distance, earnings and rider mapping against aggregator data | All | Critical | Phase 3 - Finance & Control |  | Not Started
☐ | T-042 | Operations | Orders | Build exception queue for unassigned or mismatched orders | Surface issues where order, rider or vehicle mapping fails | All | High | Phase 2 - Core Operations |  | Not Started
☐ | T-043 | Operations | Incidents | Define accident / incident operating procedure | Who escalates, who approves, what evidence is required | All | High | Phase 2 - Core Operations |  | Not Started
☐ | T-044 | Operations | Resources | Define spare / replacement vehicle dispatch logic | How fast replacement happens and who is eligible | Owned + Rented | High | Phase 2 - Core Operations |  | Not Started
☐ | T-045 | Operations | Resources | Create rider-owned breakdown support policy | Clarify when the company helps and when the rider remains responsible | Rider-Owned Only | Medium | Phase 3 - Finance & Control |  | Not Started
☐ | T-046 | Operations | Dashboard | Define operations dashboard metrics | Orders per rider, late deliveries, attendance gaps and downtime | All | Medium | Phase 4 - Integrations & BI |  | Not Started
☐ | T-047 | Fleet | Vehicle Master | Define vehicle onboarding checklist | Registration, insurance, photos, VIN/chassis and readiness check | All | Critical | Phase 1 - Foundation |  | Not Started
☐ | T-048 | Fleet | Vehicle Master | Create source-type-specific field requirements | Owned purchase data, rental contract data, rider ownership proof | All (varies by source type) | Critical | Phase 1 - Foundation |  | Not Started
☐ | T-049 | Fleet | Vehicle Master | Design supplier master for rented vehicles | Supplier contacts, contracts, rates, replacement terms and SLA | Rented Only | High | Phase 1 - Foundation |  | Not Started
☐ | T-050 | Fleet | Vehicle Master | Design owned fleet asset profile | Purchase date, capex, expected life and disposal method | Owned Only | High | Phase 1 - Foundation |  | Not Started
☐ | T-051 | Fleet | Vehicle Master | Design rider-owned approval workflow | Ownership proof, inspection, insurance and registration validation | Rider-Owned Only | Critical | Phase 1 - Foundation |  | Not Started
☐ | T-052 | Fleet | Assignments | Implement vehicle assignment history and return flow | Track every assignment, off-hire, replacement and return | All | Critical | Phase 2 - Core Operations |  | Not Started
☐ | T-053 | Fleet | Assignments | Create vehicle handover checklist | Condition, accessories, damages, odometer and acknowledgment | Owned + Rented | High | Phase 2 - Core Operations |  | Not Started
☐ | T-054 | Fleet | Maintenance | Define preventive maintenance schedule | Service intervals by km/time for company-controlled vehicles | Owned + Rented | High | Phase 3 - Finance & Control |  | Not Started
☐ | T-055 | Fleet | Maintenance | Define maintenance routing rules by source type | Supplier, internal workshop or rider responsibility | All (varies by source type) | Critical | Phase 3 - Finance & Control |  | Not Started
☐ | T-056 | Fleet | Maintenance | Capture downtime start/end and replacement requirement | Feed utilization and loss analysis | All | High | Phase 2 - Core Operations |  | Not Started
☐ | T-057 | Fleet | Compliance | Create registration / insurance / inspection expiry tracker | Block usage of non-compliant vehicles | All | Critical | Phase 1 - Foundation |  | Not Started
☐ | T-058 | Fleet | Compliance | Create return-to-supplier workflow for rented vehicles | Off-hire, condition check, penalties and closure | Rented Only | Medium | Phase 3 - Finance & Control |  | Not Started
☐ | T-059 | Fleet | Lifecycle | Define owned fleet lifecycle and replacement planning | Age, condition, utilization and disposal triggers | Owned Only | High | Phase 4 - Integrations & BI |  | Not Started
☐ | T-060 | Fleet | Inventory | Create spare pool / standby fleet logic | Which vehicles are reserved as backup and when they can be deployed | Owned + Rented | Medium | Phase 3 - Finance & Control |  | Not Started
☐ | T-061 | Fleet | Dashboard | Define fleet dashboard metrics | Utilization, downtime, aging, maintenance due and off-road count | All | Medium | Phase 4 - Integrations & BI |  | Not Started
☐ | T-062 | Finance | Commercial Model | Map revenue models by aggregator and contract | Per order, hybrid, incentives, penalties and billing cycle | All | Critical | Phase 2 - Core Operations |  | Not Started
☐ | T-063 | Finance | Commercial Model | Design client / aggregator billing rules | Who gets billed, at what rate and under what reconciliation logic | All | Critical | Phase 3 - Finance & Control |  | Not Started
☐ | T-064 | Finance | Cost Model | Build rented vehicle monthly cost model | Rent, deposit, insurance share, uncovered repairs and downtime cost | Rented Only | Critical | Phase 3 - Finance & Control |  | Not Started
☐ | T-065 | Finance | Cost Model | Build owned vehicle monthly cost model | Depreciation, insurance, registration, maintenance and downtime | Owned Only | Critical | Phase 3 - Finance & Control |  | Not Started
☐ | T-066 | Finance | Cost Model | Build rider-owned company cost model | Allowance, subsidy, compliance admin and support cost | Rider-Owned Only | High | Phase 3 - Finance & Control |  | Not Started
☐ | T-067 | Finance | Payroll | Design payroll engine formula library | Fixed pay, per-order pay, km pay, incentive, deduction and advance recovery | All (varies by source type) | Critical | Phase 3 - Finance & Control |  | Not Started
☐ | T-068 | Finance | Payroll | Map vehicle-related deductions and allowances | Different payroll treatment by vehicle source type | All (varies by source type) | Critical | Phase 3 - Finance & Control |  | Not Started
☐ | T-069 | Finance | Payables | Build supplier rental payable workflow | Rental invoice intake, matching, approval and payment schedule | Rented Only | High | Phase 3 - Finance & Control |  | Not Started
☐ | T-070 | Finance | Assets | Build depreciation schedule for owned fleet | Monthly depreciation and asset book value movement | Owned Only | High | Phase 3 - Finance & Control |  | Not Started
☐ | T-071 | Finance | Receivables | Build invoicing workflow | Billing output by period, client, aggregator and supporting detail | All | High | Phase 3 - Finance & Control |  | Not Started
☐ | T-072 | Finance | Receivables | Build collections and dispute tracker | Invoice aging, rejections and underpayment resolution | All | Medium | Phase 4 - Integrations & BI |  | Not Started
☐ | T-073 | Finance | Reporting | Define profit by vehicle source type report | Owned vs rented vs rider-owned profitability | All | Critical | Phase 4 - Integrations & BI |  | Not Started
☐ | T-074 | Finance | Reporting | Define profit by aggregator and client report | Gross margin and unit economics by contract | All | High | Phase 4 - Integrations & BI |  | Not Started
☐ | T-075 | Finance | Controls | Design month-end close checklist | Reconcile orders, payroll, fleet cost, AP, AR and incidents | All | Medium | Phase 4 - Integrations & BI |  | Not Started
☐ | T-076 | Finance | Dashboard | Define finance dashboard metrics | Revenue, gross margin, cost per delivery, payables and receivables | All | Medium | Phase 4 - Integrations & BI |  | Not Started
☐ | T-077 | Compliance | Policy Matrix | Create legal and compliance document matrix | List mandatory rider and vehicle documents by country / client / aggregator | All | Critical | Phase 1 - Foundation |  | Not Started
☐ | T-078 | Compliance | Activation Controls | Create rider activation block rules | Stop activation for expired visa, license or invalid bank / contract status | All | Critical | Phase 1 - Foundation |  | Not Started
☐ | T-079 | Compliance | Activation Controls | Create vehicle activation block rules | Stop use for expired registration, insurance or failed inspection | All | Critical | Phase 1 - Foundation |  | Not Started
☐ | T-080 | Compliance | Source-Type Controls | Define rider-owned vehicle approval controls | Proof of ownership, inspection, insurance and registration verification | Rider-Owned Only | Critical | Phase 1 - Foundation |  | Not Started
☐ | T-081 | Compliance | Source-Type Controls | Define rented vehicle supplier control requirements | Valid contract, return terms, liability terms and SLA | Rented Only | High | Phase 2 - Core Operations |  | Not Started
☐ | T-082 | Compliance | Source-Type Controls | Define owned fleet audit requirements | Asset tag, depreciation setup and maintenance plan existence | Owned Only | Medium | Phase 3 - Finance & Control |  | Not Started
☐ | T-083 | Compliance | Incidents | Create accident evidence checklist | Photos, police report, rider statement, vehicle status and recovery decision | All | High | Phase 2 - Core Operations |  | Not Started
☐ | T-084 | Compliance | Incidents | Create liability and recovery approval flow | Who decides cost recovery and what threshold requires finance approval | All (varies by source type) | High | Phase 3 - Finance & Control |  | Not Started
☐ | T-085 | Compliance | Audit Trail | Define audit log requirements | Track who changed status, rates, assignments and payroll-sensitive fields | All | High | Phase 2 - Core Operations |  | Not Started
☐ | T-086 | Compliance | Approvals | Define exception approval workflow | Temporary overrides for urgent shifts, document grace periods or replacement use | All | High | Phase 2 - Core Operations |  | Not Started
☐ | T-087 | Compliance | Records | Define document archive and retention policy | Store rider docs, contracts, vehicle docs and supplier agreements | All | Medium | Phase 2 - Core Operations |  | Not Started
☐ | T-088 | Compliance | Dashboard | Define compliance dashboard metrics | Expired docs, blocked riders, blocked vehicles and open incidents | All | Medium | Phase 4 - Integrations & BI |  | Not Started
☐ | T-089 | Integrations | Aggregator APIs | Gather API requirements for Talabat / Jahez / Keeta | Auth method, order feed, rider mapping, earnings and reconciliation data | All | Critical | Phase 2 - Core Operations |  | Not Started
☐ | T-090 | Integrations | Aggregator APIs | Design external order ID mapping strategy | Persist unique order references and source import lineage | All | Critical | Phase 2 - Core Operations |  | Not Started
☐ | T-091 | Integrations | Aggregator APIs | Design earnings / incentive import mapping | Link imported payouts to payroll and billing calculations | All | High | Phase 3 - Finance & Control |  | Not Started
☐ | T-092 | Integrations | Mobility | Define GPS / telematics integration requirements | Location, trip timing, speed, distance and route evidence | All | High | Phase 2 - Core Operations |  | Not Started
☐ | T-093 | Integrations | Mobility | Define mobile app needs for rider and supervisor | Attendance, issues, assignment view, earnings and compliance reminders | All | High | Phase 4 - Integrations & BI |  | Not Started
☐ | T-094 | Integrations | Finance Systems | Define accounting system integration scope | AP, AR, payroll journals, asset movements and cost centers | All | Medium | Phase 4 - Integrations & BI |  | Not Started
☐ | T-095 | Integrations | Documents | Define e-sign / document storage integration | Contracts, document uploads and approval evidence | All | Medium | Phase 4 - Integrations & BI |  | Not Started
☐ | T-096 | Integrations | Notifications | Create alerting requirements | Expiry alerts, breakdown alerts, blocked activation and payroll exceptions | All | High | Phase 2 - Core Operations |  | Not Started
☐ | T-097 | Integrations | Reliability | Design webhook retry and error handling | Ensure imports are idempotent, monitored and replayable | All | High | Phase 2 - Core Operations |  | Not Started
☐ | T-098 | Integrations | Reliability | Create integration monitoring checklist | Daily file/API status, failures, latency and reconciliation gaps | All | Medium | Phase 4 - Integrations & BI |  | Not Started
☐ | T-099 | BI & Reports | Metric Design | Create KPI dictionary | Define formulas, owners, grain and refresh frequency for each KPI | All | High | Phase 4 - Integrations & BI |  | Not Started
☐ | T-100 | BI & Reports | Metric Design | Define source-type profitability KPIs | Profit per owned / rented / rider-owned vehicle model | All | Critical | Phase 4 - Integrations & BI |  | Not Started
☐ | T-101 | BI & Reports | Executive Reports | Design CEO dashboard | Revenue, gross margin, active riders, source-type mix and risk counts | All | Medium | Phase 4 - Integrations & BI |  | Not Started
☐ | T-102 | BI & Reports | Executive Reports | Design weekly executive pack | Compact performance summary for leadership review | All | Low | Phase 4 - Integrations & BI |  | Not Started
☐ | T-103 | BI & Reports | Ops Reports | Define rider productivity report | Orders per rider, shift hours, acceptance and downtime impact | All | Medium | Phase 4 - Integrations & BI |  | Not Started
☐ | T-104 | BI & Reports | Ops Reports | Define idle rider / idle vehicle analysis | Find underutilized resources and pairing opportunities | Owned + Rented | Medium | Phase 4 - Integrations & BI |  | Not Started
☐ | T-105 | BI & Reports | Fleet Reports | Define fleet aging and replacement report | Owned fleet lifecycle and disposal signals | Owned Only | Medium | Phase 4 - Integrations & BI |  | Not Started
☐ | T-106 | BI & Reports | Fleet Reports | Define downtime and maintenance report | Events, hours lost, cause and replacement demand | All | Medium | Phase 4 - Integrations & BI |  | Not Started
☐ | T-107 | BI & Reports | Finance Reports | Define payroll exception report | Outliers in incentives, deductions, zero-pay and negative-pay cases | All | High | Phase 4 - Integrations & BI |  | Not Started
☐ | T-108 | BI & Reports | Finance Reports | Define billing reconciliation report | Order count, revenue, disputes and invoice support by period | All | High | Phase 4 - Integrations & BI |  | Not Started
☐ | T-109 | BI & Reports | Compliance Reports | Define compliance risk report | Upcoming expiries, blocked assets, blocked riders and unresolved incidents | All | Medium | Phase 4 - Integrations & BI |  | Not Started
Note on K5: Update status as work progresses.
Note on L5: Assign responsible person or team.
Note on M5: Optional target date for planning.
Note on N5: Use for blockers, assumptions, or links.

## Data Model
Data Model Checklist
Linked departmental view for Data Model. Edit the Master Tracker tab as the source of truth; this tab mirrors those rows for focused review.
Checklist | Task ID | Module | Workstream | Task | Deliverable / Logic | Source Type Impact | Priority | Phase | Dependency | Status | Owner | Target Date | Notes
☐ | T-001 | Data Model | Core Entities | Define master ID strategy and audit fields across all tables | Common primary keys, created/updated timestamps, soft delete and source tracking | All | Critical | Phase 1 - Foundation |  | Not Started
☐ | T-002 | Data Model | Core Entities | Create Riders entity and base profile fields | Personal details, license, visa, bank, status and rider category | All | Critical | Phase 1 - Foundation |  | Not Started
☐ | T-003 | Data Model | Core Entities | Create Vehicles entity with mixed-fleet attributes | Plate, make/model, status, compliance dates and current assignment | All | Critical | Phase 1 - Foundation |  | Not Started
☐ | T-004 | Data Model | Mixed Fleet Logic | Add vehicle_source_type enumeration | RENTED_BY_COMPANY, OWNED_BY_COMPANY, RIDER_OWNED | All | Critical | Phase 1 - Foundation |  | Not Started
☐ | T-005 | Data Model | Mixed Fleet Logic | Create Vehicle_Source_Details entity | Ownership, supplier, purchase/rent cost, responsibilities and contract dates | All (varies by source type) | Critical | Phase 1 - Foundation |  | Not Started
☐ | T-006 | Data Model | Assignments | Create Rider_Vehicle_Assignments history table | Track assignment start/end, aggregator, client and reason for reassignment | All | Critical | Phase 1 - Foundation |  | Not Started
☐ | T-007 | Data Model | Commercial Data | Create Clients entity | 3PL customer / legal entity records for multi-client support | All | High | Phase 1 - Foundation |  | Not Started
☐ | T-008 | Data Model | Commercial Data | Create Aggregators entity | Talabat, Jahez, Keeta and any future partner configuration | All | Critical | Phase 1 - Foundation |  | Not Started
☐ | T-009 | Data Model | Commercial Data | Create Contracts entity | Rates, validity dates, billing terms and service rules by client / aggregator | All | Critical | Phase 2 - Core Operations |  | Not Started
☐ | T-010 | Data Model | Operations Data | Create Shifts entity | Shift types, scheduled hours, attendance linkage and allocation rules | All | High | Phase 2 - Core Operations |  | Not Started
☐ | T-011 | Data Model | Operations Data | Create Attendance entity | GPS check-in/out, worked hours, exceptions and approval status | All | Critical | Phase 2 - Core Operations |  | Not Started
☐ | T-012 | Data Model | Operations Data | Create Orders entity | External order ID, rider, vehicle, distance, revenue, payout and source import batch | All | Critical | Phase 2 - Core Operations |  | Not Started
☐ | T-013 | Data Model | Fleet Data | Create Maintenance_Events entity | Service/repair/accident records with paid_by and recovered_from fields | All (varies by source type) | Critical | Phase 3 - Finance & Control |  | Not Started
☐ | T-014 | Data Model | Finance Data | Create Payroll entity | Fixed pay, per-order pay, allowances, deductions, advances and net pay | All (varies by source type) | Critical | Phase 3 - Finance & Control |  | Not Started
☐ | T-015 | Data Model | Finance Data | Create Finance_Ledger / cost allocation structure | Map vehicle, rider, supplier and aggregator transactions for reporting | All | High | Phase 3 - Finance & Control |  | Not Started
☐ | T-016 | Data Model | Risk & Controls | Create Incidents / accidents entity | Capture incident type, responsibility, cost recovery and downtime impact | All | High | Phase 2 - Core Operations |  | Not Started
☐ | T-017 | Data Model | Risk & Controls | Define master status enums for riders, vehicles, orders and compliance | Ensure controlled values and reusable logic across modules | All | High | Phase 1 - Foundation |  | Not Started
☐ | T-018 | Data Model | Security | Design user roles and permission matrix | HR, Ops, Fleet, Finance, Compliance, Admin and Executive access rights | All | High | Phase 1 - Foundation |  | Not Started

## HR
HR Checklist
Linked departmental view for HR. Edit the Master Tracker tab as the source of truth; this tab mirrors those rows for focused review.
Checklist | Task ID | Module | Workstream | Task | Deliverable / Logic | Source Type Impact | Priority | Phase | Dependency | Status | Owner | Target Date | Notes
☐ | T-019 | HR | Onboarding | Define rider onboarding workflow | Steps from application to activation including document approval | All | Critical | Phase 1 - Foundation |  | Not Started
☐ | T-020 | HR | Onboarding | Create rider category rules based on transport model | Different handling for company-bike riders vs rider-owned riders | All (varies by source type) | Critical | Phase 1 - Foundation |  | Not Started
☐ | T-021 | HR | Onboarding | Build document collection checklist | CPR/ID, visa, license, contract, bank, emergency contact | All | High | Phase 1 - Foundation |  | Not Started
☐ | T-022 | HR | Contracts | Prepare employment / service contract templates | Separate clauses for company vehicle, rented vehicle and rider-owned vehicle cases | All (varies by source type) | High | Phase 1 - Foundation |  | Not Started
☐ | T-023 | HR | Contracts | Capture deposit / deduction agreements where applicable | Vehicle damage, uniform, equipment or advance recovery logic | Owned + Rented | High | Phase 2 - Core Operations |  | Not Started
☐ | T-024 | HR | Compliance | Track visa and license expiry alerts | Prevent activation of riders with invalid legal documents | All | Critical | Phase 1 - Foundation |  | Not Started
☐ | T-025 | HR | Payroll Inputs | Define pay components and earning rules | Fixed salary, per-order, extra km, allowance, deductions and incentives | All (varies by source type) | Critical | Phase 2 - Core Operations |  | Not Started
☐ | T-026 | HR | Payroll Inputs | Define own-bike allowance policy | When and how rider-owned vehicle riders receive transport allowance | Rider-Owned Only | High | Phase 3 - Finance & Control |  | Not Started
☐ | T-027 | HR | Payroll Inputs | Define company-bike deduction policy | Monthly/daily deduction or damage recovery for company vehicles | Owned + Rented | High | Phase 3 - Finance & Control |  | Not Started
☐ | T-028 | HR | Attendance | Design attendance approval flow | Missed check-in, manual override, lateness and supervisor approval | All | High | Phase 2 - Core Operations |  | Not Started
☐ | T-029 | HR | People Ops | Create disciplinary process linked to vehicle misuse | Late return, reckless use, damage and repeated non-compliance | Owned + Rented | Medium | Phase 3 - Finance & Control |  | Not Started
☐ | T-030 | HR | People Ops | Create offboarding checklist | Final payroll, asset return, account disablement and document archive | All | High | Phase 3 - Finance & Control |  | Not Started
☐ | T-031 | HR | People Ops | Design leave / absence handling | Link leave status to roster and payroll | All | Medium | Phase 2 - Core Operations |  | Not Started
☐ | T-032 | HR | Dashboard | Define HR dashboard metrics | Headcount, active riders, expired docs, churn and payroll exceptions | All | Medium | Phase 4 - Integrations & BI |  | Not Started

## Operations
Operations Checklist
Linked departmental view for Operations. Edit the Master Tracker tab as the source of truth; this tab mirrors those rows for focused review.
Checklist | Task ID | Module | Workstream | Task | Deliverable / Logic | Source Type Impact | Priority | Phase | Dependency | Status | Owner | Target Date | Notes
☐ | T-033 | Operations | Shift Planning | Build shift planning and roster structure | Daily/weekly rider scheduling by client and aggregator | All | Critical | Phase 2 - Core Operations |  | Not Started
☐ | T-034 | Operations | Shift Planning | Create rider eligibility check before shift activation | Only activate riders with valid docs and approved vehicle | All | Critical | Phase 2 - Core Operations |  | Not Started
☐ | T-035 | Operations | Allocation | Design rider allocation rules by aggregator | Talabat / Jahez / Keeta assignment logic and eligibility mapping | All | Critical | Phase 2 - Core Operations |  | Not Started
☐ | T-036 | Operations | Allocation | Build rider + vehicle pairing workflow | Assign compliant available vehicle to rider for active shift | Owned + Rented | High | Phase 2 - Core Operations |  | Not Started
☐ | 36-1 | Operations | Allocation | Replace Vehicle of Rider | in case vehicle issues ability to temp./ perm replace the vehicle | Owned + Rented | High | Phase 4 - Integrations & BI |  | Not Started
☐ | T-037 | Operations | Live Control | Design live operations control tower view | Online riders, active orders, issues, idle riders and replacement needs | All | High | Phase 4 - Integrations & BI |  | Not Started
☐ | T-038 | Operations | Live Control | Create breakdown escalation workflow | Different path for owned, rented and rider-owned vehicle incidents | All (varies by source type) | Critical | Phase 2 - Core Operations |  | Not Started
☐ | T-039 | Operations | Attendance | Connect attendance to operations roster | Show no-shows, late arrivals and active shift status in ops view | All | High | Phase 2 - Core Operations |  | Not Started
☐ | T-040 | Operations | Orders | Create manual order import fallback process | CSV/manual upload when API is unavailable | All | Medium | Phase 2 - Core Operations |  | Not Started
☐ | T-041 | Operations | Orders | Define order reconciliation process | Validate order count, distance, earnings and rider mapping against aggregator data | All | Critical | Phase 3 - Finance & Control |  | Not Started
☐ | T-042 | Operations | Orders | Build exception queue for unassigned or mismatched orders | Surface issues where order, rider or vehicle mapping fails | All | High | Phase 2 - Core Operations |  | Not Started
☐ | T-043 | Operations | Incidents | Define accident / incident operating procedure | Who escalates, who approves, what evidence is required | All | High | Phase 2 - Core Operations |  | Not Started
☐ | T-044 | Operations | Resources | Define spare / replacement vehicle dispatch logic | How fast replacement happens and who is eligible | Owned + Rented | High | Phase 2 - Core Operations |  | Not Started
☐ | T-045 | Operations | Resources | Create rider-owned breakdown support policy | Clarify when the company helps and when the rider remains responsible | Rider-Owned Only | Medium | Phase 3 - Finance & Control |  | Not Started
☐ | T-046 | Operations | Dashboard | Define operations dashboard metrics | Orders per rider, late deliveries, attendance gaps and downtime | All | Medium | Phase 4 - Integrations & BI |  | Not Started

## Fleet
Fleet Checklist
Linked departmental view for Fleet. Edit the Master Tracker tab as the source of truth; this tab mirrors those rows for focused review.
Checklist | Task ID | Module | Workstream | Task | Deliverable / Logic | Source Type Impact | Priority | Phase | Dependency | Status | Owner | Target Date | Notes
☐ | T-047 | Fleet | Vehicle Master | Define vehicle onboarding checklist | Registration, insurance, photos, VIN/chassis and readiness check | All | Critical | Phase 1 - Foundation |  | Not Started
☐ | T-048 | Fleet | Vehicle Master | Create source-type-specific field requirements | Owned purchase data, rental contract data, rider ownership proof | All (varies by source type) | Critical | Phase 1 - Foundation |  | Not Started
☐ | T-049 | Fleet | Vehicle Master | Design supplier master for rented vehicles | Supplier contacts, contracts, rates, replacement terms and SLA | Rented Only | High | Phase 1 - Foundation |  | Not Started
☐ | T-050 | Fleet | Vehicle Master | Design owned fleet asset profile | Purchase date, capex, expected life and disposal method | Owned Only | High | Phase 1 - Foundation |  | Not Started
☐ | T-051 | Fleet | Vehicle Master | Design rider-owned approval workflow | Ownership proof, inspection, insurance and registration validation | Rider-Owned Only | Critical | Phase 1 - Foundation |  | Not Started
☐ | T-052 | Fleet | Assignments | Implement vehicle assignment history and return flow | Track every assignment, off-hire, replacement and return | All | Critical | Phase 2 - Core Operations |  | Not Started
☐ | T-053 | Fleet | Assignments | Create vehicle handover checklist | Condition, accessories, damages, odometer and acknowledgment | Owned + Rented | High | Phase 2 - Core Operations |  | Not Started
☐ | T-054 | Fleet | Maintenance | Define preventive maintenance schedule | Service intervals by km/time for company-controlled vehicles | Owned + Rented | High | Phase 3 - Finance & Control |  | Not Started
☐ | T-055 | Fleet | Maintenance | Define maintenance routing rules by source type | Supplier, internal workshop or rider responsibility | All (varies by source type) | Critical | Phase 3 - Finance & Control |  | Not Started
☐ | T-056 | Fleet | Maintenance | Capture downtime start/end and replacement requirement | Feed utilization and loss analysis | All | High | Phase 2 - Core Operations |  | Not Started
☐ | T-057 | Fleet | Compliance | Create registration / insurance / inspection expiry tracker | Block usage of non-compliant vehicles | All | Critical | Phase 1 - Foundation |  | Not Started
☐ | T-058 | Fleet | Compliance | Create return-to-supplier workflow for rented vehicles | Off-hire, condition check, penalties and closure | Rented Only | Medium | Phase 3 - Finance & Control |  | Not Started
☐ | T-059 | Fleet | Lifecycle | Define owned fleet lifecycle and replacement planning | Age, condition, utilization and disposal triggers | Owned Only | High | Phase 4 - Integrations & BI |  | Not Started
☐ | T-060 | Fleet | Inventory | Create spare pool / standby fleet logic | Which vehicles are reserved as backup and when they can be deployed | Owned + Rented | Medium | Phase 3 - Finance & Control |  | Not Started
☐ | T-061 | Fleet | Dashboard | Define fleet dashboard metrics | Utilization, downtime, aging, maintenance due and off-road count | All | Medium | Phase 4 - Integrations & BI |  | Not Started

## Finance
Finance Checklist
Linked departmental view for Finance. Edit the Master Tracker tab as the source of truth; this tab mirrors those rows for focused review.
Checklist | Task ID | Module | Workstream | Task | Deliverable / Logic | Source Type Impact | Priority | Phase | Dependency | Status | Owner | Target Date | Notes
☐ | T-062 | Finance | Commercial Model | Map revenue models by aggregator and contract | Per order, hybrid, incentives, penalties and billing cycle | All | Critical | Phase 2 - Core Operations |  | Not Started
☐ | T-063 | Finance | Commercial Model | Design client / aggregator billing rules | Who gets billed, at what rate and under what reconciliation logic | All | Critical | Phase 3 - Finance & Control |  | Not Started
☐ | T-064 | Finance | Cost Model | Build rented vehicle monthly cost model | Rent, deposit, insurance share, uncovered repairs and downtime cost | Rented Only | Critical | Phase 3 - Finance & Control |  | Not Started
☐ | T-065 | Finance | Cost Model | Build owned vehicle monthly cost model | Depreciation, insurance, registration, maintenance and downtime | Owned Only | Critical | Phase 3 - Finance & Control |  | Not Started
☐ | T-066 | Finance | Cost Model | Build rider-owned company cost model | Allowance, subsidy, compliance admin and support cost | Rider-Owned Only | High | Phase 3 - Finance & Control |  | Not Started
☐ | T-067 | Finance | Payroll | Design payroll engine formula library | Fixed pay, per-order pay, km pay, incentive, deduction and advance recovery | All (varies by source type) | Critical | Phase 3 - Finance & Control |  | Not Started
☐ | T-068 | Finance | Payroll | Map vehicle-related deductions and allowances | Different payroll treatment by vehicle source type | All (varies by source type) | Critical | Phase 3 - Finance & Control |  | Not Started
☐ | T-069 | Finance | Payables | Build supplier rental payable workflow | Rental invoice intake, matching, approval and payment schedule | Rented Only | High | Phase 3 - Finance & Control |  | Not Started
☐ | T-070 | Finance | Assets | Build depreciation schedule for owned fleet | Monthly depreciation and asset book value movement | Owned Only | High | Phase 3 - Finance & Control |  | Not Started
☐ | T-071 | Finance | Receivables | Build invoicing workflow | Billing output by period, client, aggregator and supporting detail | All | High | Phase 3 - Finance & Control |  | Not Started
☐ | T-072 | Finance | Receivables | Build collections and dispute tracker | Invoice aging, rejections and underpayment resolution | All | Medium | Phase 4 - Integrations & BI |  | Not Started
☐ | T-073 | Finance | Reporting | Define profit by vehicle source type report | Owned vs rented vs rider-owned profitability | All | Critical | Phase 4 - Integrations & BI |  | Not Started
☐ | T-074 | Finance | Reporting | Define profit by aggregator and client report | Gross margin and unit economics by contract | All | High | Phase 4 - Integrations & BI |  | Not Started
☐ | T-075 | Finance | Controls | Design month-end close checklist | Reconcile orders, payroll, fleet cost, AP, AR and incidents | All | Medium | Phase 4 - Integrations & BI |  | Not Started
☐ | T-076 | Finance | Dashboard | Define finance dashboard metrics | Revenue, gross margin, cost per delivery, payables and receivables | All | Medium | Phase 4 - Integrations & BI |  | Not Started

## Compliance
Compliance Checklist
Linked departmental view for Compliance. Edit the Master Tracker tab as the source of truth; this tab mirrors those rows for focused review.
Checklist | Task ID | Module | Workstream | Task | Deliverable / Logic | Source Type Impact | Priority | Phase | Dependency | Status | Owner | Target Date | Notes
☐ | T-077 | Compliance | Policy Matrix | Create legal and compliance document matrix | List mandatory rider and vehicle documents by country / client / aggregator | All | Critical | Phase 1 - Foundation |  | Not Started
☐ | T-078 | Compliance | Activation Controls | Create rider activation block rules | Stop activation for expired visa, license or invalid bank / contract status | All | Critical | Phase 1 - Foundation |  | Not Started
☐ | T-079 | Compliance | Activation Controls | Create vehicle activation block rules | Stop use for expired registration, insurance or failed inspection | All | Critical | Phase 1 - Foundation |  | Not Started
☐ | T-080 | Compliance | Source-Type Controls | Define rider-owned vehicle approval controls | Proof of ownership, inspection, insurance and registration verification | Rider-Owned Only | Critical | Phase 1 - Foundation |  | Not Started
☐ | T-081 | Compliance | Source-Type Controls | Define rented vehicle supplier control requirements | Valid contract, return terms, liability terms and SLA | Rented Only | High | Phase 2 - Core Operations |  | Not Started
☐ | T-082 | Compliance | Source-Type Controls | Define owned fleet audit requirements | Asset tag, depreciation setup and maintenance plan existence | Owned Only | Medium | Phase 3 - Finance & Control |  | Not Started
☐ | T-083 | Compliance | Incidents | Create accident evidence checklist | Photos, police report, rider statement, vehicle status and recovery decision | All | High | Phase 2 - Core Operations |  | Not Started
☐ | T-084 | Compliance | Incidents | Create liability and recovery approval flow | Who decides cost recovery and what threshold requires finance approval | All (varies by source type) | High | Phase 3 - Finance & Control |  | Not Started
☐ | T-085 | Compliance | Audit Trail | Define audit log requirements | Track who changed status, rates, assignments and payroll-sensitive fields | All | High | Phase 2 - Core Operations |  | Not Started
☐ | T-086 | Compliance | Approvals | Define exception approval workflow | Temporary overrides for urgent shifts, document grace periods or replacement use | All | High | Phase 2 - Core Operations |  | Not Started
☐ | T-087 | Compliance | Records | Define document archive and retention policy | Store rider docs, contracts, vehicle docs and supplier agreements | All | Medium | Phase 2 - Core Operations |  | Not Started
☐ | T-088 | Compliance | Dashboard | Define compliance dashboard metrics | Expired docs, blocked riders, blocked vehicles and open incidents | All | Medium | Phase 4 - Integrations & BI |  | Not Started

## Integrations
Integrations Checklist
Linked departmental view for Integrations. Edit the Master Tracker tab as the source of truth; this tab mirrors those rows for focused review.
Checklist | Task ID | Module | Workstream | Task | Deliverable / Logic | Source Type Impact | Priority | Phase | Dependency | Status | Owner | Target Date | Notes
☐ | T-089 | Integrations | Aggregator APIs | Gather API requirements for Talabat / Jahez / Keeta | Auth method, order feed, rider mapping, earnings and reconciliation data | All | Critical | Phase 2 - Core Operations |  | Not Started
☐ | T-090 | Integrations | Aggregator APIs | Design external order ID mapping strategy | Persist unique order references and source import lineage | All | Critical | Phase 2 - Core Operations |  | Not Started
☐ | T-091 | Integrations | Aggregator APIs | Design earnings / incentive import mapping | Link imported payouts to payroll and billing calculations | All | High | Phase 3 - Finance & Control |  | Not Started
☐ | T-092 | Integrations | Mobility | Define GPS / telematics integration requirements | Location, trip timing, speed, distance and route evidence | All | High | Phase 2 - Core Operations |  | Not Started
☐ | T-093 | Integrations | Mobility | Define mobile app needs for rider and supervisor | Attendance, issues, assignment view, earnings and compliance reminders | All | High | Phase 4 - Integrations & BI |  | Not Started
☐ | T-094 | Integrations | Finance Systems | Define accounting system integration scope | AP, AR, payroll journals, asset movements and cost centers | All | Medium | Phase 4 - Integrations & BI |  | Not Started
☐ | T-095 | Integrations | Documents | Define e-sign / document storage integration | Contracts, document uploads and approval evidence | All | Medium | Phase 4 - Integrations & BI |  | Not Started
☐ | T-096 | Integrations | Notifications | Create alerting requirements | Expiry alerts, breakdown alerts, blocked activation and payroll exceptions | All | High | Phase 2 - Core Operations |  | Not Started
☐ | T-097 | Integrations | Reliability | Design webhook retry and error handling | Ensure imports are idempotent, monitored and replayable | All | High | Phase 2 - Core Operations |  | Not Started
☐ | T-098 | Integrations | Reliability | Create integration monitoring checklist | Daily file/API status, failures, latency and reconciliation gaps | All | Medium | Phase 4 - Integrations & BI |  | Not Started

## BI & Reports
BI & Reports Checklist
Linked departmental view for BI & Reports. Edit the Master Tracker tab as the source of truth; this tab mirrors those rows for focused review.
Checklist | Task ID | Module | Workstream | Task | Deliverable / Logic | Source Type Impact | Priority | Phase | Dependency | Status | Owner | Target Date | Notes
☐ | T-099 | BI & Reports | Metric Design | Create KPI dictionary | Define formulas, owners, grain and refresh frequency for each KPI | All | High | Phase 4 - Integrations & BI |  | Not Started
☐ | T-100 | BI & Reports | Metric Design | Define source-type profitability KPIs | Profit per owned / rented / rider-owned vehicle model | All | Critical | Phase 4 - Integrations & BI |  | Not Started
☐ | T-101 | BI & Reports | Executive Reports | Design CEO dashboard | Revenue, gross margin, active riders, source-type mix and risk counts | All | Medium | Phase 4 - Integrations & BI |  | Not Started
☐ | T-102 | BI & Reports | Executive Reports | Design weekly executive pack | Compact performance summary for leadership review | All | Low | Phase 4 - Integrations & BI |  | Not Started
☐ | T-103 | BI & Reports | Ops Reports | Define rider productivity report | Orders per rider, shift hours, acceptance and downtime impact | All | Medium | Phase 4 - Integrations & BI |  | Not Started
☐ | T-104 | BI & Reports | Ops Reports | Define idle rider / idle vehicle analysis | Find underutilized resources and pairing opportunities | Owned + Rented | Medium | Phase 4 - Integrations & BI |  | Not Started
☐ | T-105 | BI & Reports | Fleet Reports | Define fleet aging and replacement report | Owned fleet lifecycle and disposal signals | Owned Only | Medium | Phase 4 - Integrations & BI |  | Not Started
☐ | T-106 | BI & Reports | Fleet Reports | Define downtime and maintenance report | Events, hours lost, cause and replacement demand | All | Medium | Phase 4 - Integrations & BI |  | Not Started
☐ | T-107 | BI & Reports | Finance Reports | Define payroll exception report | Outliers in incentives, deductions, zero-pay and negative-pay cases | All | High | Phase 4 - Integrations & BI |  | Not Started
☐ | T-108 | BI & Reports | Finance Reports | Define billing reconciliation report | Order count, revenue, disputes and invoice support by period | All | High | Phase 4 - Integrations & BI |  | Not Started
☐ | T-109 | BI & Reports | Compliance Reports | Define compliance risk report | Upcoming expiries, blocked assets, blocked riders and unresolved incidents | All | Medium | Phase 4 - Integrations & BI |  | Not Started

## Logic Register
Logic Register & Acceptance Checklist
Lock these rules before development. Use this sheet for validation, UAT and change control.
Rule ID | Area | Trigger / Event | Expected System Behavior | Source Type Impact | Priority | Status | Owner | Acceptance / Test Scenario
LR-001 | Rider activation | When a rider is activated for a shift | System blocks activation if visa/license/contract status is invalid | All | Critical | Not Started |  | Test rider with expired license must remain blocked
LR-002 | Vehicle activation | When a vehicle is assigned or used | System blocks use if registration/insurance/inspection is invalid | All | Critical | Not Started |  | Expired insurance should stop assignment
LR-003 | Vehicle source type | When a vehicle record is created | Every vehicle must have vehicle_source_type populated | All | Critical | Not Started |  | No vehicle can be saved without source type
LR-004 | Owned vehicle costing | During monthly costing run | Owned vehicles use depreciation + maintenance + compliance costs | Owned Only | High | Not Started |  | Book value and monthly cost should update
LR-005 | Rented vehicle costing | During monthly costing run | Rented vehicles use rental expense + uncovered repair + compliance costs | Rented Only | High | Not Started |  | Rental payable should link to vehicle
LR-006 | Rider-owned vehicle costing | During monthly costing run | Rider-owned vehicles use allowance/subsidy/support costs only | Rider-Owned Only | High | Not Started |  | No company asset cost should be posted
LR-007 | Maintenance routing | When maintenance event is logged | Responsible party auto-routes based on source type and contract terms | All (varies by source type) | Critical | Not Started |  | Supplier / company / rider routing should differ
LR-008 | Assignment history | When rider/vehicle pairing changes | System must create assignment start/end history record | All | Critical | Not Started |  | Previous assignment must close before new one opens
LR-009 | Payroll allowance/deduction | When payroll is generated | Vehicle-related earnings or deductions depend on source type | All (varies by source type) | Critical | Not Started |  | Own-bike allowance and company-bike deduction must not both apply
LR-010 | Breakdown replacement | When a vehicle becomes unavailable mid-shift | Replacement workflow differs by source type and policy | All (varies by source type) | High | Not Started |  | Rider-owned case may not auto-assign company backup
LR-011 | Order integrity | When orders are imported | Imported orders must map to rider, aggregator and source batch with exception handling | All | Critical | Not Started |  | Unmapped orders should enter exception queue
LR-012 | Billing reconciliation | Before invoice is issued | Invoice totals must tie to reconciled order and contract data | All | Critical | Not Started |  | Draft invoice blocked if unreconciled orders exist
LR-013 | Compliance override | When exception approval is used | Temporary approval must be logged with approver, reason and expiry | All | High | Not Started |  | Expired override should auto-close
LR-014 | Incident recovery | When accident cost is booked | Paid_by and recovered_from must be captured for every incident | All | High | Not Started |  | Incident without cost responsibility should be flagged
LR-015 | Profitability segmentation | When BI/reporting refresh runs | Reports must segment margin by owned, rented and rider-owned models | All | Critical | Not Started |  | Mixed-source report should reconcile to total margin